MERIDIAN BANK

Statement of Architecture Work

Retail Banking Modernisation — Digital Platform Programme

| Document reference | Version | Date | Status |
| --- | --- | --- | --- |
| SAW-2026-001 | 1.0 | 10 July 2026 | Approved |

Prepared by the Enterprise Architecture team, Office of the CIO. Fictional worked example prepared as TOGAF® 10 study material — Meridian Bank, Coastline Credit, and all names, dates, and figures are invented. TOGAF is a registered trademark of The Open Group.

# Document control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | 20 Jun 2026 | A. Reyes | Initial draft |
| 0.9 | 3 Jul 2026 | A. Reyes | Aligned to approved Architecture Vision v1.0 |
| 1.0 | 10 Jul 2026 | A. Reyes | Approved by sponsor — engagement authorised |

## Review and approval

| Role | Name | Action | Date |
| --- | --- | --- | --- |
| CIO (Sponsor) | D. Okafor | Approved | 3 Jul 2026 |
| Chief Risk Officer | S. Nakamura | Reviewed | 1 Jul 2026 |
| Head of Retail Banking | P. Costa | Reviewed | 1 Jul 2026 |
| Chief Architect | A. Reyes | Author / submitted | 26 Jun 2026 |

# 1. Title and request reference

Title: Retail Banking Modernisation — Digital Platform Programme, architecture development engagement.

This Statement of Architecture Work responds to Request for Architecture Work RAW-2026-004, issued by the Office of the CIO on 12 May 2026 following board approval of the modernisation mandate and completion of the Preliminary Phase (Organizational Model for EA v1.2; Tailored Architecture Framework v1.0). Approval of this document by the sponsor authorises the engagement and concludes Phase A.

# 2. Project description and scope

An ADM cycle covering Phases B through F to develop Business, Data, Application, and Technology architectures for the Retail Banking division, produce an Architecture Roadmap, and deliver an Implementation and Migration Plan. Implementation is governed under Phase G; changes under Phase H.

## 2.1 Scope

| Dimension | In scope | Out of scope |
| --- | --- | --- |
| Enterprise | Retail Banking division; Coastline Credit customer migration | Wealth Management; Institutional division |
| Domains | Business, Data, Application, Technology (full BDAT) | — |
| Capabilities | Deposits, lending, payments; channel integration; customer data mastering | General ledger replacement; HR and corporate systems |
| Depth | To the level required to support investment decisions and the Implementation and Migration Plan | Detailed solution design (delivery teams, under Phase G governance) |
| Time horizon | Target state 2029; transition architectures 2027 and 2028 | — |

## 2.2 Constraints

Coastline customer migration must complete by Q4 2027 (contractual). Recorded as a constraint, not a requirement, and reflected in risk identification.

CPS 230 impact tolerances apply throughout, including all transition states.

Delivery teams operate SAFe; architecture work integrates with PI cadence rather than replacing it.

Architecture budget as per approved business case MB-BC-2026-11.

# 3. Architecture Vision (reference)

The approved Architecture Vision AV-2026-001 v1.0 (3 July 2026) forms part of this Statement of Architecture Work by reference. It defines the problem, stakeholders and concerns, high-level requirements R-01 to R-06, summary target architecture, value proposition and KPIs, and transformation risks.

# 4. Managerial approach

Iteration: architecture development proceeds baseline-then-target per domain, scoped per iteration; level of detail is fit for gap analysis and impact assessment, no further.

SAFe integration: per the Tailored Architecture Framework, architecture iterations align to PI cadence; Architecture Contracts are implemented as enabler epics with compliance criteria.

Governance: the Architecture Review Board meets fortnightly; phase-end reviews gate progression; the Governance Log records all decisions and dispensations.

Requirements: managed continuously via the Requirements Management phase; disposal of a requirement occurs within the relevant phase and is recorded.

Risk: transformation risks reviewed at each ARB; CRO holds a standing seat for migration-wave sign-off.

# 5. Change of scope procedures

Any party may raise a change request against scope, constraints, or planned deliverables; requests are logged in the Governance Log.

The Chief Architect assesses impact on architecture work in flight, the roadmap, and the Q4 2027 migration constraint.

Changes within the approved budget and time horizon are decided by the Architecture Review Board.

Changes affecting budget, the migration deadline, or enterprise scope (for example further acquisitions) are escalated to the sponsor; a material enterprise-scope change triggers a revisit of the Preliminary Phase.

Approved changes produce a revised Statement of Architecture Work version; work continues against the prior version until approval.

# 6. Roles, responsibilities, and deliverables

| Role | Name | Responsibility |
| --- | --- | --- |
| Sponsor (CIO) | D. Okafor | Owns the engagement; approves SoAW and phase-end gates; resolves escalations |
| Chief Architect | A. Reyes | Leads the ADM cycle; accountable for deliverables and ARB submissions |
| Lead Business Architect | M. Haddad | Phase B; capability and value-stream models; gap analysis |
| Lead Data Architect | J. Lindqvist | Phase C (Data); customer data platform; migration data architecture |
| Lead Application Architect | K. Osei | Phase C (Application); product engines; API and event layer |
| Lead Technology Architect | R. Petrova | Phase D; technology services; dual-region resilience posture |
| CRO delegate | T. Nguyen | Risk review; CPS 230 tolerance assurance; migration-wave sign-off |
| SAFe RTE liaison | L. Marino | PI alignment; enabler epic scheduling with delivery trains |

## 6.1 Deliverables

| Phase | Deliverable | Acceptance gate |
| --- | --- | --- |
| B | Business Architecture (ADD increment); gap analysis; candidate roadmap components | ARB phase-end review |
| C | Data and Application Architectures (ADD increments); candidate roadmap components | ARB phase-end review |
| D | Technology Architecture (ADD increment); candidate roadmap components | ARB phase-end review |
| E | Consolidated Architecture Roadmap; transition architectures; work packages | ARB + sponsor review |
| F | Implementation and Migration Plan (finalised); Architecture Contracts drafted | Sponsor approval |
| Continuous | Requirements Repository maintenance; Governance Log; risk register updates | Fortnightly ARB |

# 7. Acceptance criteria and procedures

| # | Criterion |
| --- | --- |
| AC-1 | Each domain architecture demonstrates traceability from requirements (R-01 to R-06) through gaps to candidate roadmap components |
| AC-2 | All transition states are assessed against CPS 230 impact tolerances and carry CRO delegate sign-off |
| AC-3 | The Architecture Roadmap sequences migration-enabling work packages to meet the Q4 2027 constraint with schedule contingency |
| AC-4 | Every transition architecture delivers identifiable business value, not solely technical milestones |
| AC-5 | Reuse assessment (Architecture Repository, then industry reference models such as BIAN) is evidenced before any bespoke building block is proposed |
| AC-6 | Deliverables conform to the Tailored Architecture Framework templates and are lodged in the Architecture Repository |

Procedure: the Chief Architect submits each deliverable to the ARB with a self-assessment against these criteria; the ARB accepts, accepts with conditions, or returns with findings. Sponsor approval at the Phase F gate constitutes acceptance of the engagement's outputs.

# 8. Plan and schedule

| Phase | Window | PI alignment | Key milestone |
| --- | --- | --- | --- |
| B — Business Architecture | Jul – Sep 2026 | PI-3 2026 | Capability and value-stream models; gaps agreed |
| C — Information Systems | Sep – Dec 2026 | PI-4 2026 | Data platform and product-engine architectures |
| D — Technology Architecture | Dec 2026 – Feb 2027 | PI-1 2027 | Dual-region technology services defined |
| E — Opportunities and Solutions | Feb – Apr 2027 | PI-2 2027 | Roadmap consolidated; migration waves shaped |
| F — Migration Planning | Apr – Jun 2027 | PI-2/3 2027 | Implementation and Migration Plan approved |
| Migration execution (Phase G governance) | Jun – Dec 2027 | PI-3/4 2027 | Coastline migration complete by Q4 2027 |

Schedule contingency of one PI is held between the Phase F gate and the final Coastline migration wave. Any consumption of contingency is reported to the sponsor.

# 9. Approval

Approval of this Statement of Architecture Work by the sponsor authorises the architecture engagement described above and concludes Phase A of the ADM cycle.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor — Chief Information Officer | D. Okafor | (signed) | 10 Jul 2026 |
| Chief Architect | A. Reyes | (signed) | 10 Jul 2026 |